## HEALTHUB
DATE | NAME OF THE DEVELOPER | DEVELOPER WORKING ON | TIME REQUIRED TO FINISH | WORK DETAILS | STATUS | PENDING WORK (IF ANY) | REMAINING TIME TO FINISH | REMARKS
NOVEMBER
2017-11-01 | AMIT | HEALTHUB WEBSITE |  | adjusting designing error in all pages as per development requirement and analyzing the project | Completed 95% |  |  | some part will adjusted with development
2017-11-02 | AMIT | HEALTHUB WEBSITE |  | implement database connection in all design pages with more security feature | Completed
2017-11-03 | AMIT | HEALTHUB ADMIN SECTION |  | making admin panel for healthub with admin login, change password and logout with testing | Completed
2017-11-07 | AMIT | HEALTHUB ADMIN SECTION |  | make user authority dynamic edit change password with new admin security | Completed
2017-11-08 | AMIT | HEALTHUB ADMIN SECTION |  | making services list dynamic in admin panel and searching jpg png gif file upload and with resize code and testing | Completed |  |  | testing photo resize in defferent image format
2017-11-09 | AMIT | HEALTHUB ADMIN SECTION |  | Photo crop in jpg png and gif format working now. Services added with photo upload complete with edit and disable healthub | Completed |  |  | also verify and discuss the code and project of yellow pages. Giving training to student
|  |  |  | discuss with anup pragatimilk about some error and anydesk checking error | On Hold |  |  | in our all system and mobile site was run perfectly. Problem with there system may be or network
|  | HEALTHUB ADMIN SECTION |  | helthub specialization add edit delete with link in service | Completed |  |  | specilization dyanamic with photo upload complete
|  |  |  | state and disctrict added with edit n delete | Completed
2017-11-11 | AMIT | HEALTHUB ADMIN SECTION |  | complete addition of city with edit and delete | Completed
|  |  |  | making database of signup form of both patient and associative and make the store procedure | Completed
|  |  |  | seach and implement when date select calculate age automatic and check password verification and when associative option select a dropdown comes to select associative not for patient | Completed
|  |  |  | Searching for file upload from csv file to sql database directly | Continue
2017-07-13 | AMIT | HEALTHUB ADMIN SECTION |  | in registration catagorise it in patient or type of service taken and creating UID of it. Also testing csv file upload to mysql | Continue
DECEMBER
2017-12-12 | SHRABANTIKA | ADMIN CATEGORY SECTION |  | Category, Subcategory & Endcategory Added with Edit & Delete | Completed |  |  | SHRABANTIKA STARTED HEALTHUB WORK
|  | ADMIN LOCATION SECTION |  | Geo Location Added in Admin Panel with Link in State, District & City | Completed
2017-12-13 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | Doctor Form Added with Link in Associate Page | Continue
2017-12-14 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | Making Database for Doctor & Doctor Form Developed with Image and File Upload | Completed
2017-12-15 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | Login / Logout Page Implement with Dashboard Design | Completed
2017-12-16 | SHRABANTIKA | ASSOCIATE SECTION |  | Edit / Delete Page Developed for Associates | Completed
|  | ADMIN DOCTOR SECTION |  | dashboard sidenav design
edit delete page developed for doctor page
2017-12-18 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor list view developed and design doctor admin panel | Completed
2017-12-19 | SHRABANTIKA | DOCTOR DASHBOARD |  | new admin panel design for doctor | Continue
2017-12-20 | SHRABANTIKA | DOCTOR DASHBOARD |  | new admin panel design for doctor | Continue
2017-12-21 | SHRABANTIKA | DOCTOR DASHBOARD |  | new admin panel design for doctor | Completed
2017-12-22 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor form modification and changes with action page | Continue
2017-12-23 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor form modification and changes with action page and new table create and modify for doctor certificates | Completed
2017-12-26 | SHRABANTIKA | HEALTHUB ADMIN SECTION |  | new admin panel design for hadmin | Continue
2017-12-27 | SHRABANTIKA | HEALTHUB ADMIN SECTION |  | new admin panel design for hadmin | Continue
2017-12-28 | SHRABANTIKA | ADMIN CHEMIST & NURSE SECTION |  | chemist diagnosis nurse form part design | Continue
2017-12-29 | SHRABANTIKA | ADMIN CHEMIST & NURSE SECTION |  | chemist diagnosis nurse form part design | Completed
2017-12-30 | SHRABANTIKA | ADMIN CHEMIST SECTION |  | making database for chemist and chemist form developed with images and pdf upload | Completed
JANUARY
2018-01-02 | SHRABANTIKA | ADMIN DOCTOR & CHEMIST SECTION |  | doctor list view and chemist list view design and developed | Completed
2018-01-03 | SHRABANTIKA | ADMIN LOCATION SECTION |  | state and district form changes with database | Completed
|  | ADMIN DOCTOR SECTION |  | doctor form and chenmist form change with database |  |  |  | rechange database and form
2018-01-04 | SHRABANTIKA | ADMIN CHEMIST SECTION |  | address part of chemist form modification and changes with database | Completed
|  | ADMIN DOCTOR SECTION |  | address part of doctor form modification and change with database | Continue
2018-01-05 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | address part of doctor form modification | Completed
doctor form edit delete part changes
2018-01-06 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor form change with edit page | Continue
2018-01-07 | SHRABANTIKA | ADMIN DIAGNOSTIC SECTION |  | diagnostic center form developed with new data base | Continue
2018-01-08 | SHRABANTIKA | ADMIN DIAGNOSTIC SECTION |  | diagnostic center form developed with new data base | Completed
diagnostic listing with edit and delete
2018-01-09 | SHRABANTIKA | ADMIN EQUIPMENT SECTION |  | medical equipment store form design developed with database | Completed
2018-01-10 | SHRABANTIKA | ADMIN EQUIPMENT SECTION |  | medical equipment store listing with edit and delete | Completed
2018-01-11 | SHRABANTIKA | ADMIN PHYSIOTHERAPY SECTION |  | Physiotherapy form design developed with database | Continue
2018-01-12 | SHRABANTIKA | ADMIN PHYSIOTHERAPY SECTION |  | Physiotherapy form design developed with database | Completed
|  |  |  | physiotherapy form listing with edit with photo upload | Continue
2018-01-13 | SHRABANTIKA | PHYSIOTHERAPY SECTION |  | physiotherapy form listing with edit and delete | Completed
2018-01-15 | SHRABANTIKA | SIGN IN & SIGN UP |  | sign up for developed in front end with dashboard connection | Completed
2018-01-16 | No Work | [6 empty] | Absent
2018-01-17 | SHRABANTIKA | DOCTOR DASHBOARD |  | Changes in doctor dashboard after signup in frontend | Completed |  |  | discuss with client healthub about doctor part of the project
2018-01-18 | SHRABANTIKA | ADMIN PATIENT SECTION |  | patient form design and develop with new database | Continue
2018-01-19 | SHRABANTIKA | ADMIN PATIENT SECTION |  | 1st part of patient form develop for sign up and login complete | Completed
2018-01-20 | SHRABANTIKA | ADMIN PARTNER SITES |  | our partner form design develop with photo upload and listing | Completed
2018-01-22 | SHRABANTIKA | ADMIN PARTNER SITES |  | edit delete with photo upload and data design in frontend | Completed
2018-01-23 | SHRABANTIKA | WEBSITE - DOCTOR SECTION |  | design of frontend pages with the data of doctor details | Continue |  |  | discuss with client healthub about doctor dashboard part and some minor changes in design
2018-01-24 | No Work | [6 empty] | Absent
2018-01-25 | SHRABANTIKA | WEBSITE - DOCTOR SECTION |  | design of frontend pages with the data of doctor details
subcategory display in fronend scrolling
client display in frontend scrolling
2018-01-26 | No Work | [6 empty] | Republic Day
2018-01-27 | SHRABANTIKA | WEBSITE - DOCTOR SECTION |  | view page of doctor design changes with data | Completed
2018-01-28 | SHRABANTIKA | ADMIN BANKING SECTION |  | bank details form design develop with new database in master section | Completed
|  |  |  | listing of bank details with edit and delete | Completed
|  | ADMIN DOCTOR SECTION |  | display the bank data in doctor form | Completed
2018-01-29 | SHRABANTIKA | ADMIN DOCTOR SECTION & DOCTOR DASHBOARD |  | doctor profile photo change form design develop in doctor dashboard | Completed
|  |  |  | specialist added in doctor profile and dash board design change accoring to new data | Continue
2018-01-30 | SHRABANTIKA | WEBSITE - DOCTOR SECTION |  | doctor consultaion page design and developed with specialization search | Completed
2018-01-31 | SHRABANTIKA | DOCTOR DASHBOARD |  | doctor profile page design and develop in doctor dashboard | Continue
FEBRUARY
2018-02-01 | SHRABANTIKA | DOCTOR DASHBOARD |  | doctor profile page design and develop in doctor dashboard | Continue |  |  | FULL PROJECT DISCUSSION
2018-02-02 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | agreement form design develop with file upload edit and delete | Completed
2018-02-03 | SHRABANTIKA | DOCTOR DASHBOARD |  | profile page develop in doctor dassboard | Continue
2018-02-05 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | profile page edit part develop | Completed
2018-02-06 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor form with signup part develop in frontend | Continue
2018-02-07 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor form with signup part develop in frontend | Continue
|  | DOCTOR DASHBOARD |  | block calender add and display in doctor dashboard | Continue
| PRITI | ADMIN MEDICINE SECTION |  | Medicine Part form design and develop in backend | Continue |  |  | PRITI STARTED MEDICINE WORK
2018-02-08 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor form part develop in frontend | Completed
|  | DOCTOR DASHBOARD |  | block calender add and display in doctor dashboard | Completed
|  | SIGN IN & SIGN UP |  | signup form changes with password validation | Completed
|  | WEBSITE - INDEX PAGE |  | fronend design changes in index page | Completed
| PRITI | ADMIN MEDICINE SECTION |  | medicine part form design and develop with edit delete in backend | Completed
2018-02-09 | SHRABANTIKA | WEBSITE - DOCTOR SECTION |  | firstconsultation page develop with database | Completed
|  | DOCTOR CHAT SECTION |  | chat with doctor page design with new database | Continue |  |  | SHRABANTIKA STARTED DOCTOR CHAT WORK
| PRITI | ADMIN MEDICINE SECTION |  | medicine page develop | Continue
2018-02-10 | SHRABANTIKA | DOCTOR CHAT SECTION |  | chat with doctor page design and develop | Completed
|  |  |  | auto update chat content | Continue
| PRITI | ADMIN MEDICINE SECTION |  | medicine page develop with auto search field | Continue
2018-02-12 | SHRABANTIKA | DOCTOR CHAT SECTION |  | auto update chat content | Completed |  |  | discuss with client healthub about medicine part and changes in design
| PRITI | ADMIN MEDICINE SECTION |  | medicine page develop with auto search field | Completed
2018-02-13 | SHRABANTIKA | ADMIN BANKING SECTION |  | Bank details form design develop with new database in master section | Completed
| PRITI | ADMIN MEDICINE SECTION |  | composition manufacturer added if not exist | complete
2018-02-14 | SHRABANTIKA | DOCTOR CHAT SECTION |  | Doctor Chat section design and develop | Continue
2018-02-15 | SHRABANTIKA | SIGN IN & SIGN UP |  | alphaneumeric captcha developed and added to signup page | Completed
|  | DOCTOR CHAT SECTION |  | Doctor Chat section design and develop | Continue
| PRITI | WEBSITE - MEDICINE SECTION |  | Order Medicine page frontend design changes as per discussion | Continue |  |  | PRITI STARTED MEDICINE FRONTEND DESIGNING CHANGES WORK
2018-02-16 | SHRABANTIKA | DOCTOR CHAT SECTION |  | Doctor Chat section design and develop | Completed
| PRITI | WEBSITE - MEDICINE SECTION |  | order medicine page frontend design changes as per discussion | Continue
2018-02-17 | SHRABANTIKA | DOCTOR DASHBOARD |  | profile edit page changes | Continue
2018-02-19 | SHRABANTIKA | DOCTOR DASHBOARD |  | profile edit page changes | Continue |  |  | discuss with client healthub about changes in design
|  | SIGN IN & SIGN UP |  | design of signup form and other minor changes in design according to client requirement | Completed
2018-02-20 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | Doctor Form changes in backend according to new data given | Continue |  |  | SHRABANTIKA STARTED NEW DOCTOR REGISTRATION FORM DESIGNING CHANGES WORK
| PRITI | WEBSITE - MEDICINE SECTION |  | medicine search page design | Continue
2018-02-21 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form changes in backend according to new data given | Continue
|  |  |  | addition of nationality with edit and delete | Completed
|  |  |  | addition of religion with edit and delete | Completed
|  |  |  | addition of country with edit and delete | Completed
|  |  |  | addition of pincode with edit and delete | Completed
|  |  |  | changes in state according to country with edit and delete | Completed
|  |  |  | changes in district according to country with edit and delete | Completed
|  |  |  | changes in city according to country with edit and delete | Completed
| PRITI | WEBSITE - MEDICINE SECTION |  | medicine page design | Continue
2018-02-22 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form changes in backend according to new data given | Continue
| PRITI | WEBSITE - MEDICINE SECTION |  | medicine page design | Continue
2018-02-23 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form develop in backend according to new data given | Continue
2018-02-24 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form design change in backend according to new data given | Continue |  |  | discuss with client healthub about minor changes in form design and listing.
2018-02-26 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | security question form design develop with new data base and edit delete form added and developed in master section | Completed
|  |  |  | Preferred Language form design develop with new data base and edit delete form added and deleloped master section | Completed
2018-02-27 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | graduation field Form design develop with new data base and edit delete form added and deleloped master section | Completed
|  |  |  | postgraduation design develop with new data base and edit delete form added and deleloped master section | Completed
|  |  |  | grading system design develop with new data base and edit delete form added and deleloped master section | Completed
|  |  |  | education specialization design develop with new data base and edit delete form added and deleloped master section | Completed
| BISWA | HEALTHUB ADMIN SECTION |  | about page design develop with new data base and edit delete form added and deleloped master section | Completed
mission design develop with new data base and edit delete form added and deleloped master section
vision design develop with new data base and edit delete form added and deleloped master section
Our Value design develop with new data base and edit delete form added and deleloped master section
Partner General Info design develop with new data base and edit delete form added and deleloped master section
CSR design develop with new data base and edit delete form added and deleloped master section
| PRITI | WEBSITE - MEDICINE SECTION |  | medicine page design and develop and add to cart develop | Continue
2018-02-28 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | post graduation specialization field Form design develop with new data base and edit delete form added and deleloped master section | Completed
|  |  |  | course duration field Form design develop with new data base and edit delete form added and deleloped master section | Completed
|  |  |  | class-x board field Form design develop with new data base and edit delete form added and deleloped master section | Completed
|  |  |  | class-xii Board field Form design develop with new data base and edit delete form added and deleloped master section | Completed
|  |  |  | medium field Form design develop with new data base and edit delete form added and deleloped master section | Completed
| BISWA | HEALTHUB ADMIN SECTION |  | changes in about us in backend with edit delete | Completed
faq field Form design develop with new data base and edit delete form added and deleloped master section
testimonial field Form design develop with new data base and edit delete form added and deleloped master section
return and refund policy field Form design develop with new data base and edit delete form added and deleloped master section
enquiry details privacy policy field Form design develop with new data base and edit delete form added and deleloped master section
Advertising Policy field Form design develop with new data base and edit delete form added and deleloped master section
Terms Of Use field Form design develop with new data base and edit delete form added and deleloped master section
| PRITI | WEBSITE - MEDICINE SECTION |  | medicine search develop and add to cart develop | Completed
|  |  |  | medicine page search bar design | Continue
MARCH
2018-03-01 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | mark field Form design develop with new data base and edit delete form added and deleloped master section | Completed
|  |  |  | doctor form developed in backend with new scrips and ajax files | Continue
| PRITI | WEBSITE - MEDICINE SECTION |  | medicine page search bar design | Continue
2018-03-03 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | phd section added to qualification with edit delete and new database | Completed
|  |  |  | qualification section changed with new database | Completed
|  |  |  | doctor form developed in backend with new scrips and ajax files | Continue
2018-03-05 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form design in backend with all scrips and ajax files | Completed
| PRITI | WEBSITE - MEDICINE SECTION |  | medicine alternate details page design and develop | Completed
2018-03-06 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form design in backend changes according to client requirement | Continue
|  |  |  | new database create for postoffice field and develop form with edit delete file | Completed
|  |  |  | post office field added to doctor form with ajax file | Completed
| PRITI | WEBSITE - MEDICINE SECTION |  | medice information part design and develop in frontend | Completed
2018-03-07 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form design in backend changes with new script according to client requirement | Continue
2018-03-08 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form design in backend changes with new script according to client requirement | Completed
|  |  |  | doctor form develop in backend | Continue
|  |  |  | Time Agreed time picker script develop in backend | Continue
| PRITI | WEBSITE - MEDICINE SECTION |  | medicine detail multiple part design and develop in frontend | Completed
|  | ADMIN MEDICINE STOCK |  | medicine stock part design in backend | Continue
2018-03-09 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form design changes according to client requirement | Completed
|  |  |  | database design and new doctor form develop in backend | Continue
| PRITI | ADMIN MEDICINE STOCK |  | medicine stock part design in backend | Continue
|  | WEBSITE - MEDICINE SECTION |  | medicine detail design changes in frontend | Completed
2018-03-10 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form develop in backend | Continue
| PRITI | ADMIN MEDICINE STOCK |  | medicine stock part design in backend | Continue
2018-03-12 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form develop in backend | Continue
| PRITI | ADMIN MEDICINE STOCK |  | Medicine Stock Part design in backend | Continue |  |  | NOT HAPPY WITH PRITI. TALKED WITH SHRABANTIKA ABOUT PRITI'S WORK.
2018-03-13 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form develop in backend | Continue |  |  | continue due some error occurred in professional experience part
| PRITI | ADMIN MEDICINE STOCK |  | medicine stock part develop in backend | Continue
|  | WEBSITE - MEDICINE SECTION |  | design change in medicine details part | Continue
2018-03-14 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | doctor form develop in backend | Completed
|  |  |  | Tab wise form open developing in backend | Continue
| PRITI | ADMIN MEDICINE STOCK |  | medicine stock part develop in backend | Continue
2018-03-15 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | Tab wise next back button work developing in doctor form | Completed
|  |  |  | Tab wise form open developing in backend | Continue
| PRITI | WEBSITE - MEDICINE SECTION |  | a-z manufacturer part develop in frontend | Continue
2018-03-16 | SHRABANTIKA | DOCTOR REGISTRATION FORM |  | Tab wise form open developing in backend | Completed
|  | DOCTOR DASHBOARD REGISTRATION FORM |  | doctor form design and develop in doctor dashboard | Completed
| PRITI | WEBSITE - MEDICINE SECTION |  | a-z manufacturer part develop in frontend | Completed
|  | ADMIN MEDICINE STOCK |  | medicine stock part develop in backend | Continue
2018-03-17 | SHRABANTIKA | DOCTOR DASHBOARD REGISTRATION FORM |  | profile edit page design on doctor dashboard | Completed
|  |  |  | profile edit page develop on doctor dashboard | Continue
|  | WEBSITE - INDEX PAGE |  | error solve in index page all dropdown | Completed
| PRITI | ADMIN MEDICINE STOCK |  | medicine stock part develop in backendin frontend | Continue
2018-03-19 | SHRABANTIKA | DOCTOR DASHBOARD REGISTRATION FORM |  | All dropdown and tab in doctordashboard checked and solve error | Completed
|  |  |  | profile edit page with image and file develop in backend | Continue
| PRITI | ADMIN MEDICINE STOCK |  | medicine stock part develop with all dropdown from database | Continue
2018-03-20 | SHRABANTIKA | DOCTOR DASHBOARD REGISTRATION FORM |  | profile edit page with image and file develop in backend | Completed
| PRITI | ADMIN MEDICINE STOCK |  | medicine stock part develop with all dropdown from database | Continue
2018-03-21 | SHRABANTIKA | DOCTOR DASHBOARD REGISTRATION FORM |  | profile page design change in doctor dashboard | Continue
| PRITI | ADMIN MEDICINE STOCK |  | Add stock details and store details in backend | Completed
2018-03-22 | SHRABANTIKA | DOCTOR DASHBOARD REGISTRATION FORM |  | profile page design change in doctor dashboard | Completed
|  |  |  | profile listing with edit in doctor dashboard | Completed
| PRITI | ADMIN MEDICINE STOCK |  | Add stock details and store details changes in backend | Continue
2018-03-23 | SHRABANTIKA | SIGN IN & SIGN UP |  | signup form change with action page | Completed
|  | WEBSITE - INDEX PAGE |  | index page design change | Completed
|  | E-PRESCRIPTION |  | add Prescription from design with and create database table for prescription form in backend | Continue |  |  | SHRABANTIKA STARTED E-PRESCRIPTION WORK
| PRITI | ADMIN MEDICINE STOCK |  | Stock part change in backend as per discussion | Continue
2018-03-24 | SHRABANTIKA | E-PRESCRIPTION |  | crate ddatabase table for symptoms & symptoms form design with edit and delete in backend | Completed
|  |  |  | crate ddatabase table for Patient Status & Patient Status form design with edit and delete in backend | Completed
|  |  |  | crate ddatabase table for Lab Test & Lab Test form design with edit and delete in backend | Completed
|  |  |  | crate ddatabase table for Imaging Test & Imaging Test form design with edit and delete in backend | Completed
|  |  |  | crate ddatabase table for Time Duration & Time Duration form design with edit and delete in backend | Completed
|  |  |  | add Prescription from design in backend | Continue
2018-03-26 | SHRABANTIKA | E-PRESCRIPTION |  | add Prescription from design in backend | Completed
|  |  |  | add scripts for all dropdown and add more option on Prescription from in backend | Continue
|  |  |  | change datbase table and development of prescription form | Continue
2018-03-27 | SHRABANTIKA | E-PRESCRIPTION |  | reviw after form design create database and developed with edit and delete | Completed
|  |  |  | add scripts for all dropdown and add more option on Prescription from in backend | Completed
|  |  |  | auto search field added in all dropdown of prescription form in backend | Completed
|  |  |  | prescription form development | Continue
2018-03-28 | SHRABANTIKA | E-PRESCRIPTION |  | create database table for all add more options and link tables with prescription table | Completed
|  |  |  | prescription form development with database | Continue |  |  | continue due to change in prescription form
|  |  |  | prescription form change with new data and scripts | Continue
2018-03-29 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from design change with new scripts according to new data given | Continue |  |  | rechange in prescription form according to new data given
| PRITI | MEDICINE STORE DASHBOARD |  | Design dashboard for store | Continue
2018-03-30 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from change with new scripts according to new data given | Continue
|  |  |  | Create database for immunization design and develop immunization form with edit and delete | Completed
| PRITI | MEDICINE STORE DASHBOARD |  | Design dashboard for store | Continue
2018-03-31 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from design change with new scripts and new ajax file | Continue
| PRITI | MEDICINE STORE DASHBOARD |  | Design dashboard for store | Continue
APRIL
2018-04-01 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from design change with new ajax file | Continue |  |  | SUNDAY
| PRITI | MEDICINE STORE DASHBOARD |  | Design dashboard for store | Continue
2018-04-02 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from design change with new ajax file | Continue
2018-04-03 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from design change with new ajax file and and new script uses | Continue
2018-04-04 |  |  |  | No Work | -------------- |  |  | Absent
2018-04-05 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from design change with new ajax file and and new script uses | continue |  |  | continue due to internet issue
2018-04-06 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from design change with new ajax file and and new script uses | Continue |  |  | 95% work completed.
2018-04-07 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from design change with new ajax file and and new script uses | Completed
|  |  |  | prescription from develop in backend | Continue
2018-04-09 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from development in backend | Continue
2018-04-10 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from development in backend | Continue
2018-04-11 | SHRABANTIKA | E-PRESCRIPTION |  | prescription from development in backend | Continue
2018-04-12 | SHRABANTIKA | ADMIN HOSPITAL SECTION |  | Create database for hospital form design and develop hospital form with edit and delete | Completed
|  | E-PRESCRIPTION |  | Select form develop in prescription form | Completed
|  | E-PRESCRIPTION |  | prescription form develop in backend with all database table | Continue |  |  | 95% work completed.
2018-04-13 | SHRABANTIKA | E-PRESCRIPTION |  | prescription form develop in backend with all add more options and database table | Completed
|  |  |  | prescriprion listing table develop in backend | Completed
|  |  |  | prescription view page design in backend | Continue
2018-04-14 | SHRABANTIKA | E-PRESCRIPTION |  | prescription view page design and develop in backend | Continue
2018-04-16 | SHRABANTIKA | E-PRESCRIPTION |  | prescription view page design and develop in backend | Completed
|  |  |  | prescription print page design and develop in backend | Completed
|  |  |  | changes in prescriprion listing table in backend | Completed
|  |  |  | changes in prescriprion form in backend | Completed
2018-04-17 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor form and listing changes in backend | Continue
2018-04-18 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor form and listing changes in backend | Continue
2018-04-19 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor form and listing changes in backend and frontend | Continue
2018-04-20 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor form and listing changes in backend and frontend | Completed
2018-04-21 | SHRABANTIKA |  |  | No Work | -------------- |  |  | Absent
2018-04-23 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | profile page changes in frontend and frontend | Completed
| PRITI | MEDICINE STORE DASHBOARD |  | Develop dashboard for store section in frontend | Continue
2018-04-24 | SHRABANTIKA | DOCTOR AUDIO / VIDEO |  | audio video chat develop in frontend | Continue |  |  | SHRABANTIKA STARTED DOCTOR AUDIO / VIDEO WORK
| PRITI | MEDICINE STORE DASHBOARD |  | Develop dashboard for store section in frontend | Continue
2018-04-25 | SHRABANTIKA | DOCTOR AUDIO / VIDEO |  | audio video chat develop in frontend | Continue
| PRITI | MEDICINE STORE DASHBOARD |  | Develop dashboard for store section in frontend | Continue
2018-04-26 | SHRABANTIKA | DOCTOR AUDIO / VIDEO |  | audio video chat develop in frontend | Continue
| PRITI | MEDICINE STORE DASHBOARD |  | Develop dashboard for store section in frontend | Continue
2018-04-27 | SHRABANTIKA | DOCTOR AUDIO / VIDEO |  | audio video chat develop in frontend | Continue
|  | E-PRESCRIPTION |  | prescription view part change | Continue
2018-04-28 | SHRABANTIKA | E-PRESCRIPTION |  | prescription view part change | Continue
| SHRABANTIKA | DOCTOR DASHBOARD |  | Doctor profile part change in doctor dashboard | Continue
2018-04-30 | SHRABANTIKA | DOCTOR DASHBOARD |  | Doctor profile part change in doctor dashboard | Continue |  |  | discuss with client healthub about changes in form doctor and prescription.
MAY
2018-05-01 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor form error part solve and changes in doctor part | Completed
2018-05-02 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | Listing section changes with new requirement and edit and delete part developing same as doctor profile page | Continue
2018-05-03 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor view part developing same as doctor profile page | Continue
2018-05-04 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor view part developing same as doctor profile page | Continue
2018-05-05 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor view part developing same as doctor profile page | Continue
2018-05-07 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor view part developing same as doctor profile page | Continue |  |  | changes in view section
2018-05-08 | SHRABANTIKA |  |  | No Work | --------------
2018-05-09 | SHRABANTIKA |  |  | No Work | --------------
2018-05-10 | SHRABANTIKA |  |  | No Work | --------------
2018-05-11 | SHRABANTIKA | E-PRESCRIPTION |  | prescription view part change | continue |  |  | error solving
2018-05-12 | SHRABANTIKA | E-PRESCRIPTION |  | prescription view part change | continue |  |  | error solving
2018-05-14 | SHRABANTIKA | E-PRESCRIPTION |  | prescription view part change | complete |  |  | error solving
2018-05-15 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor view part developing same as doctor profile page | Continue |  |  | changes in view section
2018-05-16 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | doctor view part developing same as doctor profile page | Complete |  |  | changes in view section
2018-05-17 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | Listing section changes wdisplay in tab wise | Complete |  |  | changes in listing section
2018-05-18 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | Listing section changes display in tab wise | Continue |  |  | changes in listing section
2018-05-19 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | Listing section changes display in tab wise | Continue |  |  | changes in listing section
2018-05-21 | SHRABANTIKA | E-PRESCRIPTION |  | prescription view part change | Continue |  |  | error solving
2018-05-22 | SHRABANTIKA | E-PRESCRIPTION |  | prescription view part change | Continue |  |  | error solving
2018-05-23 | SHRABANTIKA | E-PRESCRIPTION |  | prescription view part change | Continue |  |  | error solving
2018-05-24 | SHRABANTIKA | E-PRESCRIPTION |  | prescription view part change | Continue |  |  | error solving
2018-05-25 | SHRABANTIKA | LOCATION MASTER |  | change pincode add new form with new database | complete |  |  | error solving
2018-05-26 | SHRABANTIKA | LOCATION MASTER |  | add area in location master with new database with edit and delete | complete |  |  | error solving
2018-05-28 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | change all script ajax file and adress form according to pincode and area in doctor form | Continue |  |  | error solving
2018-05-29 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | change all script ajax file and adress form according to pincode and area in doctor form | Continue |  |  | error solving
2018-05-30 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | change all script ajax file and adress form according to pincode and area in doctor form | Continue |  |  | error solving
2018-05-31 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | change all script ajax file and adress form according to pincode and area in doctor form | Continue |  |  | error solving
JUNE
2018-06-01 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | change all script ajax file and adress form according to pincode and area in doctor form | Continue |  |  | error solving
2018-06-02 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | change all script ajax file and adress form according to pincode and area in doctor form | Continue |  |  | change in form
2018-06-04 | SHRABANTIKA |  |  | No Work | --------------
2018-06-05 | SHRABANTIKA |  |  | No Work | --------------
2018-06-06 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | change all script ajax file and adress form according to pincode and area in doctor form | Complete |  |  | change in form
2018-06-07 | SHRABANTIKA | ADMIN DOCTOR SECTION |  | edit and view part change according to pincode and area | Complete |  |  | change in form
2018-06-08 | SHRABANTIKA | DOCTOR DASHBOARD |  | change doctor form in doctor dashboard according to change in ppincode and area | Continue |  |  | change in form
2018-06-09 | SHRABANTIKA | DOCTOR DASHBOARD |  | change doctor form in doctor dashboard according to change in ppincode and area | Completed |  |  | change in form
2018-06-11 | SHRABANTIKA | ADMIN PATIENT SECTION |  | create new database for patient section and design patient form | Completed
2018-06-12 | SHRABANTIKA | ADMIN PATIENT SECTION |  | develop patient form in backend with small listing in patient list | Completed
2018-06-13 | SHRABANTIKA | ADMIN PATIENT SECTION |  | listing of patient details and patient view form design in backend | Continue
2018-06-14 | SHRABANTIKA | ADMIN PATIENT SECTION |  | patient view form design in backend | Completed
2018-06-15 | SHRABANTIKA | ADMIN PATIENT SECTION |  | patient view form develop in backend | Completed
2018-06-18 | SHRABANTIKA | PATIENT DASHBOARD SECTION |  | sign in changes according to patient data and design patient dashboard | Completed
2018-06-19 | SHRABANTIKA | PATIENT DASHBOARD SECTION |  | profile section develop and design in patient dashboard | Continue
2018-06-20 | SHRABANTIKA | PATIENT DASHBOARD SECTION |  | profile section develop and design in patient dashboard completed & chemist form design in backend | Continue
2018-06-21 | SHRABANTIKA | PATIENT DASHBOARD SECTION |  | set new database for chemist & chemist form design in backend | Continue
2018-06-22 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form design and set all scripts in backend | Continue
2018-06-23 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form design and set all scripts in backend | Continue
2018-06-25 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form design and set all scripts in backend | Complete
2018-06-26 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form develop tabwise in backend | Continue
2018-06-27 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form develop tabwise in backend | completed
|  |  |  | chemist form listing in backend | Continue
2018-06-28 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form listing in backend | Continue
2018-06-29 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part design | Complete
2018-06-30 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part develop | Continue
JULY
2018-07-02 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part develop | Continue
2018-07-03 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part develop | Continue
2018-07-04 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part develop | Continue
2018-07-05 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part develop | Continue
2018-07-06 | SHRABANTIKA |  |  | No Work | --------------
2018-07-07 | SHRABANTIKA |  |  | No Work | --------------
2018-07-09 | SHRABANTIKA |  |  | No Work | --------------
2018-07-10 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part develop | Continue
2018-07-11 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part develop | Continue
2018-07-12 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part develop | Continue
2018-07-13 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part develop | Continue
2018-07-14 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part develop | Continue
2018-07-17 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist form view part develop | Completed
2018-07-18 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | chemist sign up profile part edit | Completed
2018-07-19 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | making database for medicine information and medicine information form developed with edit and delete option | Completed
|  | ADMIN MEDICINE SECTION |  | making database for composition and composition form developed with edit and delete option and link with medicine information | Completed
2018-07-20 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | making database for Manufacture and Manufacture form developed with edit and delete option | Completed
|  | ADMIN MEDICINE SECTION |  | making database for medicine and medicine form developed with edit and delete option | Continue
2018-07-21 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | medicine form developed with edit and delete option | Continue
2018-07-23 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | medicine form developed with edit and delete option | Continue
2018-07-24 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | medicine stock part form developed with edit and delete option | Continue
2018-07-25 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | medicine stock part form developed with edit and delete option | Continue
2018-07-26 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | medicine stock part form developed with edit and delete option | Continue
2018-07-27 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | medicine stock part form developed with edit and delete option | Continue
2018-07-28 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | medicine stock part form developed with edit and delete option | Continue
2018-07-30 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | medicine stock part form developed with edit and delete option | Continue
2018-07-31 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | medicine form composition part develop and order medicine page in front end develop | Continue
AUGUST
2018-08-01 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | medicine dispay part develop in fronted with all calculation | Continue
2018-08-02 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | medicine dispay part develop in fronted with all calculation | Complete
2018-08-03 | SHRABANTIKA | ADMIN STOCK SECTION |  | medicine puchase part design and develop | Continue
2018-08-04 | SHRABANTIKA | ADMIN STOCK SECTION |  | purchase form develop with all calculation | Continue
2018-08-06 | SHRABANTIKA | ADMIN MEDICINE STOCK SECTION |  | purchase form develop with all calculation | Complete
|  |  |  | stock report develop in backend | Complete
2018-08-07 | SHRABANTIKA | ADMIN MEDICINE STOCK SECTION |  | Sales form develop with all calculation | Complete
|  |  |  | stock report for sale develop in backend | Continue
2018-08-08 | SHRABANTIKA | ADMIN MEDICINE STOCK SECTION |  | stock report for sale develop in backend | Complete
|  | ADMIN MEDICINE SECTION |  | medicine edit and delete section change with composition | Complete
|  | WEBSITE - MEDICINE SECTION |  | a-z manufacture page develop in frontend | Complete
|  | WEBSITE - MEDICINE SECTION |  | include new pagination in medicine details section | Complete
2018-08-09 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | medicine page develop in frontend | Continue
|  | WEBSITE - MEDICINE SECTION |  | medicine search box develop with ajax file | Continue
2018-08-10 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | medicine page develop in frontend | Continue
|  | WEBSITE - MEDICINE SECTION |  | medicine search box design and develop with ajax file and add to cart button | Continue
2018-08-11 | SHRABANTIKA | WEBSITE - HEADER SECTION |  | Location part design and develop like medplus | Complete
|  | WEBSITE - MEDICINE SECTION |  | medicine part addto cart page develop in frontend | Continue
2018-08-13 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | medicine cart detail develop in frontend with calculation | Continue
2018-08-14 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | medicine order checkout page develop | Continue
2018-08-16 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | cart-details page design and develop | Continue
2018-08-17 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | cart-details all page design and develop | Continue
2018-08-18 | SHRABANTIKA |  |  | No Work | --------------
2018-08-20 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | cart-details total calculation with discount and design page for prescription upload part | Continue
2018-08-21 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | calculation with couponin cart details page and vheckout page design | Continue
2018-08-22 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page design with all tabs | Continue
2018-08-23 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page design and develop with all tabs | Continue
2018-08-24 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page design and develop with prescription upload | Continue
2018-08-25 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page design and develop with all tabs | Continue
2018-08-27 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page design and develop with all tabs | Continue
2018-08-28 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page design and develop with all tabs | Continue
2018-08-29 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page design and develop with all tabs | Continue
|  | ADMIN STOCK SECTION |  | speed delivery form added in mastersetting with edit | Complete
|  |  |  | Payment option added in backend with edit and delete option | Complete
2018-08-30 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page design and develop with all tabs | Continue
2018-08-31 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page promotion details and prescription details part develop | Continue
SEPTEMBER
2018-09-01 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page promotion details and prescription details part develop | Continue
2018-09-03 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page shipping details part develop | Continue
2018-09-04 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page shipping details part and calculation in final tab develop | Continue
2018-09-05 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page shipping details part change and develop | Continue
2018-09-06 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout page final calculation part develop | Continue
2018-09-07 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | checkout with all tab develop | Complete
2018-09-08 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | shipping billing details tab change | Continue
2018-09-11 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | shipping billing details tab change | Complete
|  |  |  | confirmation details tab change | Continue
2018-09-12 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | confirmation details tab change | Complete
2018-09-14 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | medicine purchase and sale form design and list part design in chemist dashboard | Complete
2018-09-15 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | medicine purchase form part develop with edit and delete and purchase list developed | Complete
2018-09-17 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | medicine sale form part develop with edit and delete and purchase list developed | Continue
2018-09-18 | SHRABANTIKA | WEBSITE - HEADER SECTION |  | Location part develop like medplus | Continue
|  |  |  | Location part develop like medplus with different effects and scripts | Continue
2018-09-19 | SHRABANTIKA | WEBSITE - HEADER SECTION |  | Location part develop like medplus with different effects and scripts | Continue
2018-09-20 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | medicine sale form part develop with edit and delete and purchase list developed | Complete
|  |  |  | order list part design in chemist dash board section | Complete
|  |  |  | order list part develop in chemist dashboard | Continue
2018-09-21 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | store pickup part develop in chemist dashboard | Complete
|  |  |  | Home delivery part develop in chemist dashboard | Continue
2018-09-22 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Home delivery part develop in chemist dashboard | Complete
2018-09-24 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | All order list design changes in chemist dashboard | Continue
2018-09-25 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Chemist stock part design and develop with calculation | Continue
2018-09-26 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Chemist stock part design and develop with calculation | Complete
|  |  |  | All order part design change | Complete
2018-09-27 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Changes in checkout page and solving error | Complete
|  |  |  | medicine details page develop | Continue
2018-09-28 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Changes in checkout page and solving error | Continue
|  |  |  | medicine search page develop | Complete
2018-09-29 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Changes in checkout page and solving error | Continue
OCTOBER
2018-10-01 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Changes in purchase part in chemist dashboard | Continue
|  | ADMIN STOCK SECTION |  | create database for perchase from permission in hadmin and develop the form with edit and delete | Complete
2018-10-02 | SHRABANTIKA |  |  | No Work | --------------
2018-10-03 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | change in purchase part design with all ajax file in chemist dashboard | Complete
2018-10-04 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Purchase part form price calculation and developing according to new form | Continue
2018-10-05 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Purchase part form price calculation and developing according to new form | Complete
|  |  |  | listing of purchase details with different phase | Complete
|  |  |  | changes in stockdetails according to new data | Complete
|  |  |  | changes in sale item according to new data | Continue
2018-10-06 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | changes in ajax file and develop sell item according to new data | Continue
2018-10-08 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | changes in ajax file and develop sell item according to new data | Complete
2018-10-09 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | calculation of tax and price in sales item part accoring to new data | Complete
|  |  |  | stock section listing including sales data | Complete
2018-10-10 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | implement of new pagination in all list section of chemist dashboard | Complete
2018-10-11 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Error solving in all forms and list of chemist dashboard | Continue
2018-10-12 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Error solving in all forms and change in price calculation and remove discount amount from purchase section | Complete
2018-10-13 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | changes in price and tax part of purchase and sale section of chemist dashboard | Continue
2018-10-15 | SHRABANTIKA |  |  | No Work | --------------
2018-10-16 | SHRABANTIKA |  |  | No Work | --------------
2018-10-17 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | rechanges in purchase section and calculation part in purchase according to new data given | Continue
2018-10-18 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | rechanges in purchase form developing according to new data given | Continue
2018-10-20 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | rechanges in purchase form developing and listing according to new data given | Continue
2018-10-22 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | rechanges in purchase form developing and listing with stock according to new data given | Complete
2018-10-23 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | rechanges in sale form developing and listing with stock according to new data given | Continue
2018-10-24 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | rechanges in sale form developing and listing with stock according to new data given | Complete
|  | ADMIN MEDICINE SECTION |  | Changes in manufacturer database table and develop manufacturer form with edit and delete option according to new data | Complete
|  | ADMIN MEDICINE SECTION |  | Develop coupon section in hadmin with edit and delete | Complete
2018-10-25 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | Changes in purchase form and developing in H-admin section according to new data given | Continue
2018-10-26 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | Changes in purchase form and developing in H-admin section according to new data given | Complete
|  | ADMIN MEDICINE SECTION |  | Changes in sales form and developing in H-admin section according to new data given | Continue
2018-10-27 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | Changes in sales form and developing and listing in H-admin section according to new data given | Complete
2018-10-29 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | Changes in Healthub stock details part and calculate total stock | Complete
|  |  |  | Store wise stock section details part design and develop | Continue
2018-10-30 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | Store wise stock section details part design and develop | Complete
|  | WEBSITE - MEDICINE SECTION |  | Error solving in medicine search and order medicine | Continue
31-10-2018 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | LIsting of order medicine section with different part | Continue
NOVEMBER
2018-11-01 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | LIsting of order medicine section with different part | Continue
2018-11-02 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | medicine form change with edit and delete with new database | Complete
|  |  |  | chemist form change with edit and delete in hadmin section | Complete
|  | CHEMIST DASHBOARD SECTION |  | chemist form change with edit and delete in chemist dashboard section | Complete
|  |  |  | chemistprofile part change with edit and delete in chemist dashboard section | Complete
2018-11-03 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | Ayurvedic medicine add with edit and delete section design and developing | Continue
2018-11-05 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | Ayurvedic medicine add with edit and delete section design and developing | Continue
2018-11-06 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | Ayurvedic medicine add with edit and delete section design and developing | Continue
2018-11-08 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | Ayurvedic medicine add with edit and delete section design and developing | Complete
|  | ADMIN MEDICINE SECTION |  | Homeopathic medicine add with edit and delete section design and developing | Complete
2018-11-09 | SHRABANTIKA | WEBSITE - MEDICINE SECTION |  | Error solving in medicine search and order medicine | Continue
2018-11-10 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | order medicine format part develop in hadmin | Continue
2018-11-12 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | order medicine format part develop in hadmin | Continue
2018-11-13 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | order medicine request format part develop in hadmin | Continue
2018-11-14 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | order medicine request format part develop in customer medicine section | Continue
2018-11-15 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | order medicine request format part develop in customer medicine section with rating | Continue
2018-11-16 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | order medicine request format total order part design and develop in customer medicine section with rating | Continue
2018-11-17 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | order medicine request format total order part design and develop in customer medicine section with rating | complete
|  | CUSTOMER DASHBOARD SECTION |  | order medicine request format total order part design and develop in customer medicine section with review | continue
19-11-2018 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | order medicine request format total order part design and develop in customer medicine section with review and link with chemist dashboard | continue
20-11-2018 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | order medicine request format total order part design and develop in chemist medicine section | continue
21-11-2018 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | order medicine request format total order part design and develop in chemist medicine section link with customer dastboard | continue
22-11-2018 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | order medicine request format total order part design and develop in chemist medicine section link with customer dastboard | continue
23-11-2018 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | order medicine request format total order part design and develop in chemist medicine section link with customer dastboard | continue
24-11-2018 | SHRABANTIKA | ADMIN MEDICINE SECTION |  | Reason of cancelation form design and develop in hadmin section with edit and delete | complete
|  | CHEMIST DASHBOARD SECTION |  | order medicine request format cancellation part develop in cemist dashboard section | complete
26-11-2018 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | dashboard design and develop according to new message | complete
|  | ADMIN MEDICINE SECTION |  | Meseesage For user form design and develop with edit and delete | complete
27-11-2018 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | changes li medicine request format and develop in medicine staus on order format part in chemist dashboard | complete
28-11-2018 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | Prescription added to order medicine format and order details format with view | complete
|  | CHEMIST DASHBOARD SECTION |  | add agreement tab added in profile section of chemist dashboard | complete
|  | CUSTOMER DASHBOARD SECTION |  | rating part develop in customer order format | continue
29-11-2018 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | rating part develop in customer order format | continue
|  | CHEMIST DASHBOARD SECTION |  | change in Prescription added to order medicine format and order details format with view | complete |  |  | files are not uploaded due to rating part work is not completed
|  | CHEMIST DASHBOARD SECTION |  | change in add agreement tab added in profile section of chemist dashboard | complete
30-11-2018 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | automatic medicine cancel after 24 hour part develop in chemist dashboard section | complete
|  | CUSTOMER DASHBOARD SECTION |  | cancel part develop in customer order format | continue
DECEMBER
2018-12-01 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | cancel part develop in customer order format | Continue
|  | CHEMIST DASHBOARD SECTION |  | change in automatic medicine cancel after 15 minute part develop in chemist dashboard section | complete
2018-12-03 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | cancel part develop in customer order format | Complete
|  |  |  | review with rating part develop in customer order format | Continue
2018-12-04 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | review with rating part develop in customer order format | Continue
|  | CHEMIST DASHBOARD SECTION |  | agreement part testing and error solving | Complete
|  | ADMIN DASHBOARD SECTION |  | agreement part testing and error solving | Complete
2018-12-05 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | rating part develop in chemist dashboard section | Complete
|  |  |  | after order cancelled by customer chemist order format develop in chemist dashboard | Continue
2018-12-06 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | after order cancelled by customer chemist order format develop in chemist dashboard | Complete
|  | CUSTOMER DASHBOARD SECTION |  | review with rating part develop in customer order format | Continue
2018-12-07 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | review with rating part develop in customer order format | Complete
|  | CUSTOMER DASHBOARD SECTION |  | review with rating part develop in customer order format | Complete
|  | CHEMIST DASHBOARD SECTION |  | error solve in store pickup section | Complete
|  | CUSTOMER DASHBOARD SECTION |  | error solve in order details store pickup section | Complete
2018-12-08 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | error solve in order request format section in both chemist and customer dashboard section | Complete
2018-12-10 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | cancel part develop in customer order format and link with chemist dashboard | Continue
2018-12-11 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | Order request format section develop and display in hadmin | Continue
2018-12-12 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | Order request format section develop in all section and display in hadmin | Continue
2018-12-13 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | After automatic cancel from chemist section order display in admin section with accept and cancel part develop in hadmin section | Continue
2018-12-14 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | after order accept by hadmin all process of medicine delivery develop in hadmin section | Continue
2018-12-15 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | after order accept by hadmin all process of medicine delivery develop in hadmin section | Continue
2018-12-17 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | develop order accept and delivered by admin section | Complete
|  | ADMIN DASHBOARD SECTION |  | after automatic cancellation admin can resend that order request to any chemist of that area part developing | Continue
18-12-2018 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | after automatic cancellation admin can resend that order request to any chemist of that area part developing | Complete
|  | CHEMIST DASHBOARD SECTION |  | After resend order from hadmin section all order format develop in chemist setion | Continue
19-12-2018 | SHRABANTIKA | PATIENT DASHBOARD SECTION |  | After cancellation from hadmin orderlist and cancel list part develop in customer dashboard section | Continue
20-12-2018 | SHRABANTIKA | PATIENT DASHBOARD SECTION |  | After cancellation from hadmin orderlist and cancel list part develop in customer dashboard section | Complete
|  | ADMIN DASHBOARD SECTION |  | home delivery part develop in admin section with review and rating of both chemist and customer | Continue
21-12-2018 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | home delivery part develop in admin section with review and rating of both chemist and customer | Complete
|  |  |  | Store pickup section developed in admin section | Continue
22-12-2018 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | Store pickup section developed in admin section with all status update and rating | Continue
24-12-2018 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | Store pickup section developed in admin section with all status update and rating | Complete
|  |  |  | total order section developed in hadmin section | Continue
26-12-2018 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | total order section developed in hadmin section | complete
|  |  |  | Cancel order section developed in hadmin section | complete |  |  | testing in both admin dashboard, chemist dashboard and customer dashboard is not completed
27-12-2018 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | medicine order online testing and solve error in each page of order medicine in website patient dashboard section chemist dashboard section and admin dashboard section | continue
28-12-2018 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | inactive store section develop in both hadmin and chemist dashboard section | complete
|  |  |  | notification part develop in admin dashboard section | continue
29-12-2018 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | notification part develop in admin dashboard section | continue
2018-12-31 | SHRABANTIKA |  |  | No Work | --------------
JANUARY
2019-01-02 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | notification part develop in admin dashboard section | complete
|  | CHEMIST DASHBOARD SECTION |  | notification part develop in admin dashboard section | continue
2019-01-03 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | notification part develop in chemist dashboard section | complete
|  | CUSTOMER DASHBOARD SECTION |  | notification part develop in customer dashboard section | continue
2019-01-04 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | notification part develop in customer dashboard section | complete
|  | ADMIN DASHBOARD SECTION |  | earning and payment part develop in hadmin section | continue
2019-01-05 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | notification part develop in admin dashboard section | continue
2019-01-07 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | notification part develop in admin dashboard section | continue
2019-01-08 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | changes in purchase section in chemist dashboard | continue
2019-01-09 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | changes in purchase section in chemist dashboard | continue |  |  | continue due to calculation part is not completed
2019-01-10 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | changes in purchase section in chemist dashboard | continue
2019-01-11 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | calculation in stock section with new data and medicine expire date | continue
2019-01-12 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | calculation in stock section with new data and medicine expire date | continue
2019-01-14 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | earning and payment part develop in hadmin section | continue
2019-01-15 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | earning and payment part develop in hadmin section | continue
2019-01-16 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | earning and payment part cod, store pickup, online payment and total payment calculation part develop in hadmin section | complete
2019-01-17 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | earning and payment purchase from healthub list developed with calculation | complete
|  | ADMIN DASHBOARD SECTION |  | chemist sharing page database set design and develop with edit and delete | continue
2019-01-18 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | chemist sharing page database set design and develop with edit and delete | complete
|  | ADMIN DASHBOARD SECTION |  | earning and payment purchase from healthub list developed with calculation | complete
19-01-2019 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | earning and payment purchase from healthub list developed with calculation with date | continue
21-01-2019 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | earning and payment purchase from healthub list developed with calculation with date | complete
|  | ADMIN DASHBOARD SECTION |  | payment collect section develop in admin section | continue
22-01-2019 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | payment collect section develop in admin section | continue |  |  | continue due to some error in jquery file
23-01-2019 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | payment collect section develop in both purchase from healthub and purchase from other in admin section | continue
24-01-2019 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | payment collect section develop in both purchase from other and purchase from other calender wise in admin section | continue
25-01-2019 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | mail id entry dynamic with add edit delete with listing and select section dynamic in admin section | continue
28-01-2019 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | mail id entry dynamic with add edit delete with listing and select section dynamic in admin section | continue
29-01-2019 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | mail id entry dynamic with add edit delete with listing and select section dynamic in admin section | complete
|  |  |  | medicine order online testing and solve error in each page of order medicine in website patient dashboard section chemist dashboard section and admin dashboard section | continue
30-01-2019 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | changes in mail id entry dynamic with add edit delete with listing and select section dynamic in admin section | complete
FEBRUARY
2019-02-01 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | integrating dynamic mail id in using php mailer with mail format in each notification section | continue
2019-02-02 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | integrating dynamic mail id in using php mailer with mail format in each notification section | continue
2019-02-04 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | integrating dynamic mail id in using php mailer with mail format in each notification section | continue
2019-02-05 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | dynamic mail id integrating in each section of order medicine section on hadmin , chemist and customer dashboard section | continue
2019-02-06 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | dynamic mail id integrating in each section of order medicine section on hadmin , chemist and customer dashboard section | continue
2019-02-07 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | dynamic mail id integrating in each section of order medicine section on hadmin , chemist and customer dashboard section | continue
2019-02-08 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | dynamic mail id integrating in each section of cancel medicine section on hadmin , chemist and customer dashboard section | continue
2019-02-09 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | dynamic mail id integrating in each section of cancel medicine section on hadmin dashboard section | continue
2019-02-11 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | design changes of dynamic mail id integrating in each section of cancel medicine section on hadmin dashboard section | continue
2019-02-12 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | design changes of dynamic mail id integrating in each section of cancel medicine section on hadmin dashboard section | continue
2019-02-13 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | integrating dynamic mail id in using php mailer with mail format in each notification section | continue
2019-02-14 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | integrating dynamic mail id in using php mailer with mail format in each notification section | continue
2019-02-15 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | design changes of dynamic mail id integrating in each section of cancel medicine section on hadmin dashboard section | continue
2019-02-16 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | design changes dynamic mail id integrating in each section of order medicine section on hadmin , chemist and customer dashboard section | continue
2019-02-18 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | design changes dynamic mail id integrating in each section of order medicine section on hadmin , chemist and customer dashboard section | continue
2019-02-19 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | checking chemist registration section and error solve in each section add notification for new registration | continue
|  | ADMIN DASHBOARD SECTION |  | changes in agreement section for all associates | Completed
2019-02-20 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | checking chemist registration section and error solve in each section of chemist dashboard hadmin section with integrating php mailer | continue
2019-02-21 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | checking chemist registration section and error solve in each section of chemist dashboard hadmin section with integrating php mailer | continue
2019-02-22 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | activation part added in sign up form and changein database accoding to new data both chemist dashboard and hadmin section | continue
2019-02-23 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | activation part added in sign up form and changein database accoding to new data both chemist dashboard and hadmin section | continue
|  | ADMIN DASHBOARD SECTION |  | payment collect section develop in admin section | continue
25-02-2019 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | payment collect section develop in admin section and coolect notification part develop in chemist dashboard section | complete
2019-02-26 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | activation part added in sign up form and changein database accoding to new data both chemist dashboard and hadmin section | complete
|  | CHEMIST DASHBOARD SECTION |  | profile edit part checking all errors and solve in both hadmin section and chemist dashboard section | continue
27-02-2019 | SHRABANTIKA | CHEMIST DASHBOARD SECTION |  | profile edit part checking all errors and solve in both hadmin section and chemist dashboard section | complete
|  | CUSTOMER DASHBOARD SECTION |  | profile edit part checking all errors and solve in both hadmin section and customer dashboard section | Continue
28-02-2019 | SHRABANTIKA | CUSTOMER DASHBOARD SECTION |  | profile edit part checking all errors and solve in both hadmin section and customer dashboard section | Continue
|  | WEBSITE - SIGNUP SECTION |  | Signup form change according to condition for mail | Continue
MARCH
2019-03-01 | SHRABANTIKA |  |  | No Work | --------------
2019-03-02 | SHRABANTIKA | WEBSITE - SIGNUP SECTION |  | Signup form change according to condition for mail | Continue
2019-03-04 | SHRABANTIKA | WEBSITE - SIGNUP SECTION |  | Signup form change according to condition for mail | Continue
2019-03-05 | SHRABANTIKA | WEBSITE - SIGNUP SECTION |  | Signup form change according to condition for mail | Continue
2019-03-06 | SHRABANTIKA | WEBSITE - SIGNUP SECTION |  | Signup form change according to condition for mail | Continue
2019-03-07 | SHRABANTIKA | WEBSITE - SIGNUP SECTION |  | Signup form change according to condition for mail | Complete
|  | ADMIN DASHBOARD SECTION |  | set data base for general product , design and develop form for general products | Continue
2019-03-08 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | set data base for general product category, design and develop form for general product category with edit and delete | Complete
|  | ADMIN DASHBOARD SECTION |  | set data base for general product sub category, design and develop form for general product subcategory with edit and delete | Complete
|  | ADMIN DASHBOARD SECTION |  | set data base for general product endcategory, design and develop form for general product endcategory with edit and delete | Complete
2019-03-09 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | set data base for general product brand, design and develop form for general product brand with edit and delete | Complete
|  | ADMIN DASHBOARD SECTION |  | set data base for general product , design and develop form for general product with edit and delete | Continue
|  | WEBSITE SIGNUP SECTION |  | change all mail format for chemist and customer registration and activation | Conmplete
2019-03-11 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | set data base for general product , design and develop form for general product with edit and delete | Continue
2019-03-12 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | set data base for general product , design and develop form for general product with edit and delete | Continue
2019-03-13 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | set data base for general product , design and develop form for general product with edit and delete | Continue
2019-03-14 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | set data base for general product , design and develop form for general product with edit and delete | Continue
2019-03-15 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | set data base for general product , design and develop form for general product with edit and delete | Continue
2019-03-16 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | set data base for general product , design and develop form for general product with edit and delete online testing for add and delete product | Complete
2019-03-18 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | general product purchase form develop in admin dashboard section | Continue
2019-03-19 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | general product purchase form develop in admin dashboard section | Continue
2019-03-20 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | general product purchase form develop in admin dashboard section | complete
2019-03-21 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | general product final purchase form develop and listing in admin dashboard section | complete

## KABADIWALE
DATE | NAME OF THE DEVELOPER | DEVELOPER WORKING ON | TIME REQUIRED TO FINISH | WORK DETAILS | STATUS | PENDING WORK (IF ANY) | REMAINING TIME TO FINISH | REMARK
MARCH

## ENJOE
DATE | NAME OF THE DEVELOPER | DEVELOPER WORKING ON | TIME REQUIRED TO FINISH | WORK DETAILS | STATUS | PENDING WORK (IF ANY) | REMAINING TIME TO FINISH | REMARKS
MARCH
2019-03-25 | SHRABANTIKA | PARTNER DASHBOARD SECTION |  | remove banking information from professional and financial info and develop the form using new database | complete
|  |  |  | design change all all heading in professional and financial info section just like profile page and change the font size , background color and small designing error | complete
2019-03-26 | SHRABANTIKA | PARTNER DASHBOARD SECTION |  | change in share a lead form make event name and place of event auto search field | complete
|  |  |  | solve the issue of add and remove button | complete
|  |  |  | change the delete option in share a lead setion | complete
|  |  |  | change small designing issue in feedback form | complete
|  |  |  | change the designation field to your service and make the field dynamic dropdown fetch data from services in feedback form | complete
2019-03-27 | SHRABANTIKA | PARTNER DASHBOARD SECTION |  | change in share a lead form make event name autosearch field with fetching data from category section except the specific category recomended service | complete
|  | PARTNER DASHBOARD SECTION |  | small designing changes in profile pages | complete
|  | ADMIN DASHBOARD SECTION |  | changes in admin section in list of more info in partner list remove banking information from list | complete
|  | PARTNER DASHBOARD SECTION |  | change in professional and financial info form add a new dynamic dropdown field in Financial Information with admore option and develop the form | continue
2019-03-28 | SHRABANTIKA | PARTNER DASHBOARD SECTION |  | change in professional and financial info form add a new dynamic dropdown field in Financial Information with admore option and develop the form | continue
2019-03-29 | SHRABANTIKA | PARTNER DASHBOARD SECTION |  | change in professional and financial info form add a new dynamic dropdown field in Financial Information with admore option and develop the form | continue
2019-03-30 | SHRABANTIKA | PARTNER DASHBOARD SECTION |  | change in professional and financial info form add a new dynamic dropdown field in Financial Information with admore option and develop the form | continue
APRIL
2019-04-01 | SHRABANTIKA | PARTNER DASHBOARD SECTION |  | change in professional and financial info form add a new dynamic dropdown field in Financial Information with admore option and develop the form | complete
|  | ADMIN DASHBOARD SECTION |  | question added to popup box | complete
|  |  |  | linked question is diplay in answer table | complete
|  |  |  | create database for question enquiry type and develeop the form with edit and delete | complete
|  |  |  | change add question form with new enquiry type field and develop the form | complete
2019-04-02 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | developing form for export data for partner list | continue
|  | WEBSITE SECTION |  | Solve the problme of previous and submit button in question answer section | continue
2019-04-03 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | developing form for export data for partner list | continue
2019-04-04 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | developing form for export data for partner list | complete
2019-04-05 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | developing form for export data for Individual user list | complete
|  |  |  | developing form for export data for corporate user list | complete
|  |  |  | developing form for export data for Institutional user list | complete
|  |  |  | developing share a lead notification and individual shared a lead list | complete
|  | WEBSITE SECTION |  | add calender section to the end of question answer section and develop the form | complete
2019-04-06 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | Title Change from Venyou to enjoe admin | complete
|  |  |  | Login Id Change to admin@enjoe.in | complete
|  |  |  | add new database for login slider and develop the form with edit and delete | complete
|  | WEBSITE SECTION |  | add Enjoe title in login page | complete
|  |  |  | develop login slider | complete
|  | USER DASHBOARD SECTION |  | remove refer a friend section from profile part | complete
|  |  |  | Add testimonial section : Heading Name change, fetch address from data base and make readonly, content name change to Write Your review | complete
|  |  |  | Client Speak section : Heading Name change,Event name auto search field, content name change to give your feed back | complete
|  |  |  | Success story section : Heading Name change,remove readonly from name field, designation change to Event name with fix value Wedding Event, if address field not empty the it is readonly otherwise it is edited field, small image change to upload weding image, content name chane to share your story with us. | complete
|  |  |  | remove link from welcome with name in header part | complete
|  |  |  | Add Refer a friend tab below success story | complete
|  | PARTNER DASHBOARD SECTION |  | add title enjoe in every page in partner dashboard | complete
2019-04-08 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | change in share a lead notification and individual shared a lead list | complete
|  |  |  | developing all notification section success stories , partners feedback, customer review with mailing system | continue
2019-04-09 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | developing all notification section success stories , partners feedback, customer review with mailing system | complete
|  |  |  | change view feed back design and customer dashboard menu design | complete
2019-04-10 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | develop listing of question answer section with a given design | continue
2019-04-11 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | develop listing of question answer section with a given design | complete
2019-04-12 | SHRABANTIKA | ADMIN DASHBOARD SECTION |  | edit and delete button in view answer details | complete
|  |  |  | develop notification section in header for event enquiry | complete
|  |  |  | develop export button in view answer details | complete
|  |  |  | changes in partner feedback details and also in index page | complete
|  | USER DASHBOARD SECTION |  | develop questuion answer list in user dashboard section | complete
2019-04-13 | SHRABANTIKA | WEBSITE SECTION |  | error solving in question answer section | continue
2019-04-15 | SHRABANTIKA | WEBSITE SECTION |  | error solving in question answer section | continue
2019-04-16 | SHRABANTIKA | ADMIN SECTION |  | set data base for new category under services develop the file with corresponding ajax file and develop edit delete field | continue
|  | PARTNER ADMIN SECTION |  | change in developing for Professional & Financial info section | continue
2019-04-17 | SHRABANTIKA | ADMIN SECTION |  | set data base for new category under services develop the file with corresponding ajax file and develop edit delete field | complete
|  | PARTNER ADMIN SECTION |  | change in developing for Professional & Financial info section | continue
18-04-20196 | SHRABANTIKA | PARTNER ADMIN SECTION |  | change in developing for Professional & Financial info section | complete
19-04-20196 | SHRABANTIKA | PARTNER ADMIN SECTION |  | develop for Financial info section in partner dashboard section accoring to new changes | continue
|  | PARTNER ADMIN SECTION |  | re-change in developing for Professional & Financial info section | complete
|  | ADMIN SECTION |  | changes in partner more information section in admin section | continue
20-04-2019 | SHRABANTIKA | ADMIN SECTION |  | social link section change in both admin and website section with edit form | complete
|  | PARTNER ADMIN SECTION |  | develop for Financial info section in partner dashboard section accoring to new changes | continue
22-04-2019 | SHRABANTIKA | PARTNER ADMIN SECTION |  | develop for Financial info section in partner dashboard section accoring to new changes | complete
23-04-2019 | SHRABANTIKA | ADMIN SECTION |  | develop for Financial info section in dashboard section accoring to new changes both proffessional and financial info | complete
24-04-2019 | SHRABANTIKA | WEBSITE SECTION |  | put blog section on header part according to new deisign and add new design pages of blog section | complete
|  | ADMIN SECTION |  | develop each part of blog section with new database with edit and delete section | continue
25-04-2019 | SHRABANTIKA | ADMIN SECTION |  | develop each part of blog section with new database with edit and delete section | complete
|  | WEBSITE SECTION |  | develop blog section in front end blog page | complete
|  | USER DASHBOARD SECTION |  | develop blog form in user section with new database with edit and delete | continue
26-04-2019 | SHRABANTIKA | USER DASHBOARD SECTION |  | develop blog form in user section with new database with edit and delete | continue
|  | ADMIN SECTION |  | changes in develop each part of blog section with new database with edit and delete section | continue
27-04-2019 | SHRABANTIKA | ADMIN SECTION |  | changes in develop each part of blog section with new database with edit and delete section | continue
30-04-2019 | SHRABANTIKA | ADMIN SECTION |  | ceate new database for blogcategory develop add blog category with edit and delete | complete
|  | ADMIN SECTION |  | changes in add blog both in form and database add catagory in blog form | complete
|  | WEBSITE SECTION |  | develop the blocg category section make it dynamic | complete
|  | WEBSITE SECTION |  | make blog inner page dynamic | complete
MAY
2019-05-01 | SHRABANTIKA | WEBSITE SECTION |  | changes in website blog section accoring to new data | complete
|  | WEBSITE SECTION |  | developing user blog form in website section | continue
2019-05-02 | SHRABANTIKA | WEBSITE SECTION |  | developing user blog form in website section | complete
|  | WEBSITE SECTION |  | change in developing of blog inner page in website section | complete
2019-05-13 | SHRABANTIKA | WEBSITE SECTION |  | developing user blog form in website section and make permission in hadmin section to show the blog | continue
2019-05-14 | SHRABANTIKA | WEBSITE SECTION |  | developing user blog form in website section and make permission in hadmin section to show the blog | continue
2019-05-15 | SHRABANTIKA | WEBSITE SECTION |  | setting blog category permission and blog popular permission in website blog section | continue
2019-05-16 | SHRABANTIKA | WEBSITE SECTION |  | setting blog category permission and blog popular permission in website blog section | continue
2019-05-17 | SHRABANTIKA | WEBSITE SECTION |  | developing blog inner page | continue
2019-05-18 | SHRABANTIKA | WEBSITE SECTION |  | developing blog inner page | continue
2019-05-20 | SHRABANTIKA | WEBSITE SECTION |  | developing blogcomment section in blog inner page | continue
2019-05-21 | SHRABANTIKA | WEBSITE SECTION |  | change in blog inner page design accoring to photo addition and developing chage with new condition | continue
2019-05-22 | SHRABANTIKA | WEBSITE SECTION |  | developing like people in blog section and give your comment section in blog inner page | continue
2019-05-23 | SHRABANTIKA | WEBSITE SECTION |  | developing like people in blog section and give your comment section in blog inner page | continue
2019-05-24 | SHRABANTIKA | WEBSITE SECTION |  | developing like people in blog section and give your comment section in blog inner page | continue
2019-05-25 | SHRABANTIKA |  |  | No Work | -------------- |  |  | Absent
2019-05-27 | SHRABANTIKA | ADMIN SECTION |  | changes in notification blog section in and blog notification section | continue
2019-05-28 | SHRABANTIKA | ADMIN SECTION |  | changes in notification blog section in and blog notification section | continue
2019-05-29 | SHRABANTIKA |  |  | No Work | -------------- |  |  | Absent
2019-05-30 | SHRABANTIKA | WEBSITE SECTION |  | changes in notification blog section in and blog notification section | complete |  |  | After testing file will uploded in server
2019-05-31 | SHRABANTIKA | WEBSITE SECTION |  | change in blog form in website section and admin section | continue
JUNE
2019-06-01 | SHRABANTIKA | ADMIN SECTION |  | add multiple images in both admin and website section and change database and work flow for blog section according to given changes | continue
2019-06-03 | SHRABANTIKA | ADMIN SECTION |  | add multiple images in both admin and website section and change database and work flow for blog section according to given changes | continue
2019-06-04 | SHRABANTIKA | WEBSITE SECTION |  | developing blog section in website section and changes in blog form | continue
2019-06-05 | SHRABANTIKA | WEBSITE SECTION |  | developing blog section in website section and changes in blog form | continue
2019-06-06 | SHRABANTIKA | WEBSITE SECTION |  | developing blog section in website section and changes in blog form | continue
2019-06-07 | SHRABANTIKA | ADMIN SECTION |  | create new data base for advertisement page and design form for advertise ment developing file with edit delete option | continue
2019-06-08 | SHRABANTIKA | ADMIN SECTION |  | create new data base for advertisement page and design form for advertise ment developing file with edit delete option | continue
2019-06-10 | SHRABANTIKA | ADMIN SECTION |  | send advertisement to all mail id section designing and developing in admin section | continue
2019-06-11 | SHRABANTIKA | ADMIN SECTION |  | send advertisement to all mail id section designing and developing in admin section | complete
2019-06-12 | SHRABANTIKA | ADMIN SECTION |  | add date field in every list section in admin panel and listing data desending order | continue
2019-06-13 | SHRABANTIKA | ADMIN SECTION |  | add date field in every list section in admin panel and listing data desending order | continue |  |  | timing(8am-4pm)
2019-06-14 | SHRABANTIKA | PARTNER SECTION |  | changes in partner dashboard section in all file according to given data through email | continue |  |  | timing(8am-4pm)
2019-06-17 | SHRABANTIKA | PARTNER SECTION |  | changes in partner dashboard section in all file according to given data through email | continue
2019-06-18 | SHRABANTIKA | PARTNER SECTION |  | changes in partner dashboard section in all file according to given data through email | continue
2019-06-19 | SHRABANTIKA | PARTNER SECTION |  | changes in partner dashboard section in all file according to given data through email | continue
2019-06-20 | SHRABANTIKA | PARTNER SECTION |  | changes in partner dashboard section in all file according to given data through email | continue
2019-06-21 | SHRABANTIKA | PARTNER SECTION |  | changes in partner dashboard section in all file according to given data through email | continue
2019-06-22 | SHRABANTIKA | PARTNER SECTION |  | changes in partner dashboard section in all file according to given data through email | continue |  |  | timing(8am-5pm)
2019-06-24 | SHRABANTIKA | PARTNER SECTION |  | Refer a vendor section with coupon added dynamically developed in admin section | continue |  |  | timing(8am-5pm)
2019-06-25 | SHRABANTIKA | PARTNER SECTION |  | Refer a vendor section with coupon added dynamically developed in admin section | continue |  |  | timing(8am-5pm)
2019-06-26 | SHRABANTIKA | PARTNER SECTION |  | Refer a vendor section with coupon added dynamically developed in admin section | continue |  |  | timing(8am-5pm)
2019-06-27 | SHRABANTIKA | PARTNER SECTION |  | Refer a vendor section with coupon added dynamically developed in admin section | continue |  |  | timing(8am-5pm)
2019-06-28 | SHRABANTIKA | PARTNER SECTION |  | Refer a vendor section with coupon added dynamically developed in admin section | continue |  |  | timing(8am-5pm)
2019-06-29 | SHRABANTIKA | PARTNER SECTION |  | Referal code and refer vender develop with new module | continue |  |  | timing(8am-5pm)
JULY
2019-07-01 | SHRABANTIKA | PARTNER SECTION |  | Referal code and refer vender develop with new module | continue
2019-07-02 | SHRABANTIKA | USER SECTION |  | changes in uder dashboard section in all file according to given data through email | continue
2019-07-03 | SHRABANTIKA | USER SECTION |  | changes in uder dashboard section in all file according to given data through email | continue |  |  | timing(8am-5pm)
2019-07-05 | SHRABANTIKA | USER SECTION |  | changes in uder dashboard section in all file according to given data through email | complete
2019-07-06 | SHRABANTIKA | CORPORATE SECTION |  | changes in uder dashboard section in all file according to given data through email | continue |  |  | timing(8am-5pm)
2019-07-08 | SHRABANTIKA | CORPORATE SECTION |  | changes in uder dashboard section in all file according to given data through email | continue
2019-07-09 | SHRABANTIKA | CORPORATE SECTION |  | changes in uder dashboard section in all file according to given data through email | continue
2019-07-10 | SHRABANTIKA | CORPORATE SECTION |  | changes in uder dashboard section in all file according to given data through email | complete
2019-07-11 | SHRABANTIKA | USER SECTION |  | changes in uder dashboard section in all file according to given data through email | complete
2019-07-12 | SHRABANTIKA | WEBSITE SECTION |  | changes in question answer form development and listing | continue
|  | USER DASHBOARD SECTION |  | changes in user dashboard section given by telephonic conversation | complete
2019-07-13 | SHRABANTIKA | WEBSITE SECTION |  | changes in question answer form development and listing | complete |  |  | timing(8am-5pm)
2019-07-15 | SHRABANTIKA | ADMIN SECTION |  | changes in blog section in vadmin with multiple image addition | continue
2019-07-16 | SHRABANTIKA | WEBSITE SECTION |  | changes in blog section in vadmin with multiple image addition | continue
2019-07-17 | SHRABANTIKA | WEBSITE SECTION |  | changes in blog section in vadmin with multiple image addition | complete
2019-07-18 | SHRABANTIKA | WEBSITE SECTION |  | blog page develop with slider search by category, like share part | continue
2019-07-19 | SHRABANTIKA | WEBSITE SECTION |  | blog page develop with slider search by category, blog enquiry part develop | complete
2019-07-20 | SHRABANTIKA | WEBSITE SECTION |  | changes in blog page and blog inner page | complete |  |  | timing(8am-5pm)
|  | USER DASHBOARD SECTION |  | profile page changes in corporate and institution dashboard section | continue
2019-07-22 | SHRABANTIKA | WEBSITE SECTION |  | share blog with different social media page develop | continue
2019-07-23 | SHRABANTIKA | WEBSITE SECTION |  | share blog with different social media page develop | continue
2019-07-24 | SHRABANTIKA | ADMIN SECTION |  | advertisement section changes in admin section added advetisement category to each section | complete
2019-07-25 | SHRABANTIKA | ADMIN SECTION |  | changes in send mail footer section in advertisement notification for blog newsletter | complete
2019-07-26 | SHRABANTIKA | WEBSITE SECTION |  | error solving in blog news letter part and add email design to blog nesletter form | complete
2019-07-27 | SHRABANTIKA | ADMIN SECTION |  | changes in question answer view and view details part in admin section with new database | continue |  |  | timing(8am-5pm)
2019-07-29 | SHRABANTIKA | ADMIN SECTION |  | changes in question answer view and view details part in admin section with new database | complete
2019-07-30 | SHRABANTIKA | ADMIN SECTION |  | unsubscribe part developing in each mail sectiom | complete
2019-07-31 | SHRABANTIKA | ADMIN SECTION |  | add cancel and complete part in question answer section in admin section | continue
AUGUST
2019-08-01 | SHRABANTIKA | ADMIN SECTION |  | add cancel and complete part in question answer section in admin section | continue
2019-08-02 | SHRABANTIKA | ADMIN SECTION |  | add cancel and complete part in question answer section in admin section | continue
2019-08-03 | SHRABANTIKA | ADMIN SECTION |  | add cancel and complete part in question answer section in admin section | continue |  |  | timing(8am-5pm)
2019-08-05 | SHRABANTIKA | ADMIN SECTION AND USER SECTION |  | add cancel and complete part in question answer section in admin section | complete
2019-08-06 | SHRABANTIKA | ADMIN SECTION |  | create new data base for caterring category sub category end category and catering form design with edit and delete in admin section | continue
2019-08-07 | SHRABANTIKA | ADMIN SECTION |  | create new data base for caterring category sub category end category form design with edit and delete in admin section | complete
2019-08-08 | SHRABANTIKA | ADMIN SECTION |  | create new data base for caterring form with edit delete and display in front page | continue
2019-08-09 | SHRABANTIKA | ADMIN SECTION |  | create new data base for caterring form with edit delete and display in front page | complete
|  | WEBSITE SECTION |  | create new data base for enjoefood form with edit delete and display in front page | continue
2019-08-10 | SHRABANTIKA | ADMIN SECTION |  | create new data base for enjoefood form with edit delete and display in front page | continue |  |  | timing(8am-5pm)
2019-08-12 | SHRABANTIKA | ADMIN SECTION |  | create new data base for enjoefood form with edit delete and display in front page | continue
2019-08-13 | SHRABANTIKA | ADMIN SECTION |  | create new data base for enjoefood form with edit delete and display in front page | complete
|  |  |  | notification for order food in admin section with listing view | complete
2019-08-14 | SHRABANTIKA | ADMIN SECTION |  | add estimated price in order food section in data base | complete |  |  | timing(8am-5pm)
|  |  |  | mail added to each section developed in enjoe food | continue
2019-08-16 | SHRABANTIKA | ADMIN SECTION |  | mail added to each section developed in enjoe food | continue
2019-08-17 | SHRABANTIKA | USER DASHBOARD SECTION |  | mail added to each section developed in enjoe food | complete |  |  | timing(8am-5pm)
|  |  |  | accept cancel button developed in user dashboard section in enjoe food | continue
2019-08-19 | SHRABANTIKA | USER DASHBOARD SECTION |  | accept cancel button developed in individual and corporate user dashboard section in enjoe food | complete
|  |  |  | accept cancel button developed in institutional user dashboard section in enjoe food | continue
2019-08-20 | SHRABANTIKA | USER DASHBOARD SECTION |  | accept cancel button developed in institutional user dashboard section in enjoe food | complete
2019-08-21 | SHRABANTIKA | ADMIN SECTION |  | Advertisement details addtion change in admin dashboard section | complete
2019-08-22 | SHRABANTIKA | ADMIN SECTION |  | add authority and page permission to admin section | continue
2019-08-23 | SHRABANTIKA | ADMIN SECTION |  | add authority and page permission to admin section | continue
|  | WEBSITE SECTION |  | changes in enjoe food section with developing popup images | complete
2019-08-24 | SHRABANTIKA | ADMIN SECTION |  | add authority and page permission to admin section | continue
2019-08-26 | SHRABANTIKA | ADMIN SECTION |  | changes in add authority and page permission to admin section | continue
2019-08-27 | SHRABANTIKA | ADMIN SECTION |  | changes is photo upload section and edit food setion in enjoe food addition form | continue
2019-08-28 | SHRABANTIKA | ADMIN SECTION |  | changes is enjoe food section and rearrange the food in squential order | continue
2019-08-29 | SHRABANTIKA | ADMIN SECTION |  | create new database for dynamic menu section and develop menu category form with edit and delete condition | continue
2019-08-30 | SHRABANTIKA | ADMIN SECTION |  | create new database for dynamic menu section and develop menu category form with edit and delete condition | complete
2019-08-31 | SHRABANTIKA | ADMIN SECTION |  | create new database for dynamic page section and develop page form with edit and delete condition and develop page permision in header section | continue
SEPTEMBER
2019-09-03 | SHRABANTIKA | ADMIN SECTION |  | adding all pages to data base for page permission of authority with edit and delete condition | continue
2019-09-04 | SHRABANTIKA | ADMIN SECTION |  | adding all pages to data base for page permission of authority with edit and delete condition | continue
2019-09-05 | SHRABANTIKA | ADMIN SECTION |  | adding all pages to data base for page permission of authority with edit and delete condition | continue
2019-09-06 | SHRABANTIKA | ADMIN SECTION |  | create database for new user for authority and develop page permission to new user | continue
2019-09-07 | SHRABANTIKA | ADMIN SECTION |  | create database for new user for authority and develop page permission to new user | continue
2019-09-09 | SHRABANTIKA | ADMIN SECTION |  | create database for new user for authority and develop page permission to new user | complete
|  | ADMIN SECTION |  | changes in header section according to new database and new authority system | continue
2019-09-10 | SHRABANTIKA | ADMIN SECTION |  | changes in header section according to new database and new authority system | complete
2019-09-11 | SHRABANTIKA | WEBSITE SECTION |  | change in enjoe food section with new temporary table connection for user login | continue
2019-09-12 | SHRABANTIKA | WEBSITE SECTION |  | change in enjoe food section with new temporary table connection for user login | continue
2019-09-13 | SHRABANTIKA | WEBSITE SECTION |  | enjoe food section with temporary table food insert for user login section modification | continue
2019-09-14 | SHRABANTIKA | WEBSITE SECTION |  | enjoe food section with temporary table food insert for user login section modification | continue
2019-09-16 | SHRABANTIKA | ADMIN SECTION |  | change in view enjoe food section in both admin and user dashboard section | continue
2019-09-17 | SHRABANTIKA | ADMIN SECTION |  | change in view enjoe food section in both admin and user dashboard section | continue
2019-09-18 | SHRABANTIKA | ADMIN SECTION |  | change and develop in view enjoe food section in corporate and institution user dashboard section with new database | continue
2019-09-19 | SHRABANTIKA | ADMIN SECTION |  | change and develop in view enjoe food section in corporate and institution user dashboard section with new database | complete
2019-09-20 | SHRABANTIKA | ADMIN SECTION |  | create new database for enjoe banner add enjoe banner form with edit delete view option | complete
|  | ADMIN SECTION |  | changes in parter agreement section chananges in partner dash board for disable agreement from list | continue
2019-09-21 | SHRABANTIKA | ADMIN SECTION |  | changes in parter agreement section chananges in partner dash board for disable agreement from list | complete
|  | ADMIN SECTION |  | changes in parter resigistraion section with new database with edit delete section | continue |  |  | (timing 8am - 5pm)
2019-09-23 | SHRABANTIKA | ADMIN SECTION |  | changes in parter resigistraion section with new database with edit delete section | complete